For your information, we are planning to carry out pre surface dressing road repairs along the roads listed below. The roads will be closed for the duration to ensure that we can carry out our works safely.

Phase 1: 12 to 21 October 2022

U5621 Bedfield Road, Monk Soham and Monk Soham Road, Bedfield

Diversion - Earl Soham Road, Town Corner, Bedfield Road, A1120, Low Road, Earl Soham, Low Road, Ashfield Cum Thorpe, The Street, Low Road, Monk Soham, Spring Road and vice versa

Phase 2: 21 to 28 October 2022

U5620 School Road, Monk Soham

Diversion - Church Road, Low Road, Spring Road and vice versa

Phase 3: 26 October to 4 November 2022

C540 Oakfields, Kenton Road, Hall Road, Monk Soham and C540 from C533 to parish boundary, Bedingfield

Diversion - Hall Road, Church Corner, Road from C533 to C531, The Street, Kenton Road, Eye Road, Low Road, Church Road, The Green and vice versa

As we plan roadworks in advance, we schedule extra days to allow for bad weather or other delays beyond our control. If we need to make major changes to our work dates, we will update the information signs on site.

A plan showing the diversion route for these works is attached to this email. When we close the road and put a diversion in place, the route needs to be accessible to vehicles of all shapes and sizes. We make our diversions as clear as possible by placing appropriate signing along the route. The latest updates on our works can be found on our website at "Temporary road closures for Suffolk Highways roadworks” and on One.Network website.

There may be times that essential emergency works are required to take place on the highway network without advanced notice – you can follow Suffolk Highways on Twitter for the latest emergency roadwork updates.

Please could you use any contacts within your division or parish to circulate this notification. Please contact us on 0345 606 6171 if you have any questions.

Suffolk Highways

www.suffolk.gov.uk/highways